## Sheet1
Task Name | Duration | Start
Requirements
-Create Requirements Doc
--Identify Input Functions | 30m
--Identify Output Functions | 30m
--Identify Storage Functions | 30m
--Identify Control Functions | 30m
-Create Use Case Diagram | 2hrs
Design
-DB Design
--Database relationship diagram | 1hr
--Entity Relationship Diagram | 1hr
--Data flow diagram | 1hr
--Context diagram | 1hr
--Build Tables
---Client | 30m
---Employee | 30m
---Children | 30m
---Medical | 30m
---Food | 30m
---Allergies | 30m
---Billing | 30m
---Rates | 30m
---Alerts | 30m
---Incidents | 30m
---Events | 30m
--Normalize Tables | 2hrs
-Design Module
--Employee | 30m
--Client | 30m
--Children | 30m
--Search/Query | 1hr
-UI Design
--Create Wireframes | 2hrs
Build
-Setup software on teams computers
--Setup version control | 30m
--Download and setup language verifiers | 1hr
-Build the program
--Setup a repository in GitHub | 30m
--Assign projects based on design and resources | 30m
---Database
----Build the modules for the database | 10days
----Feed test data into each module after completed | 2hrs
---Web app | 10days
---PHP | 10days
Test
-Create Test Data | 1hr
-Test Cases
--Yield known results | 2hrs
--Unknown Results | 8hrs
--Process Flow | 2hrs
--Edits | 8hrs